## Dashboard
Forge: feature tracker
Counts come from the Features sheet and update when you change Status or add rows.
Total | Done | Partial | Not started | % done
By area
Area | Done | Partial | Not started | Total | % done
Editing
Navigation
Workbench
Terminal
Language servers
Source control
Debugging
Extensions
Text and files
Highlighting
Packaging
Total
Open items by priority
Priority | Partial | Not started | Open
High
Medium
Low
Done but not run in the app
(Verified = Tests or Not verified)

## Features
ID | Area | Feature | Status | Priority | Verified | Notes | Owner | Updated
F-001 | Editing | Multi-cursor editing | Done |  | App | Ctrl+D / Ctrl+Alt+Up/Down / Ctrl+Shift+L |  | 2026-10-30
F-002 | Editing | Find and replace in file | Done |  | App |  |  | 2026-10-30
F-003 | Editing | Find and Replace in Files | Done |  | App |  |  | 2026-10-30
F-004 | Editing | Code folding | Done |  | App |  |  | 2026-10-30
F-005 | Editing | Snippets | Done |  | App | Prefix + Tab, popup, tab stops, mirrors, choices, variables, transforms; see F-104 to F-110 |  | 2026-10-30
F-006 | Editing | Format Document | Done |  | App | Needs a language server; per-language tab size is used |  | 2026-10-30
F-007 | Editing | Format Selection | Partial | Medium | Not verified | Builds and sends rangeFormatting; never tried against a running language server |  | 2026-10-30
F-008 | Editing | Organize Imports | Partial | Medium | Not verified | Builds and sends source.organizeImports; never tried against a running language server |  | 2026-10-30
F-009 | Editing | Auto Save (afterDelay / onFocusChange) | Done |  | App | Saves only the file in front (afterDelay); format on save is not run by it |  | 2026-10-30
F-010 | Editing | Per-language settings ([lang] blocks) | Partial | Low | Tests | Only editor.tabSize / insertSpaces / formatOnSave are read; other settings are global |  | 2026-10-30
F-011 | Editing | Word wrap and minimap | Done |  | App |  |  | 2026-10-30
F-012 | Editing | Emmet (HTML, JSX, CSS; Tab to expand) | Done |  | App | A practical subset: no filters, no lorem, fewer CSS abbreviations |  | 2026-10-30
F-013 | Editing | Spell checking | Not started | Low |  |  |  | 2026-10-30
F-014 | Editing | Sticky scroll | Done |  | App | From folding regions; hidden with word wrap on |  | 2026-10-30
F-015 | Editing | Linked editing (auto rename paired tags) | Done |  | App | HTML, XML, JSX; not for other linked ranges a server might offer |  | 2026-10-30
F-016 | Editing | Drag and drop of text | Not started | Medium |  |  |  | 2026-10-30
F-017 | Editing | Bookmarks | Not started | Low |  |  |  | 2026-10-30
F-018 | Editing | Snippets in the completion popup | Done |  | App | Language-server completions are still plain text (F-110) |  | 2026-10-30
F-019 | Navigation | Quick Open and Command Palette | Done |  | App |  |  | 2026-10-30
F-020 | Navigation | Go to Symbol / Line / Bracket | Done |  | App |  |  | 2026-10-30
F-021 | Navigation | Go Back / Go Forward (Alt+Left/Right) | Done |  | App |  |  | 2026-10-30
F-022 | Navigation | Reopen Closed Editor (Ctrl+Shift+T) | Done |  | App |  |  | 2026-10-30
F-023 | Navigation | Open Recent (Ctrl+R) | Done |  | App |  |  | 2026-10-30
F-024 | Navigation | Zen mode | Done |  | App | Hides side bar and panel only |  | 2026-10-30
F-025 | Navigation | Compare two files | Done |  | App | Uses git diff --no-index; git must be installed |  | 2026-10-30
F-026 | Navigation | Outline (symbol picker) | Partial | Medium | App | Picker only; no permanent tree view |  | 2026-10-30
F-027 | Navigation | Workspace symbol search (Ctrl+T) | Not started | Medium |  | Needs workspace/symbol request and an overlay |  | 2026-10-30
F-028 | Navigation | Peek Definition / References | Not started | Medium |  |  |  | 2026-10-30
F-029 | Navigation | Call Hierarchy and Type Hierarchy | Not started | Low |  |  |  | 2026-10-30
F-030 | Navigation | Search Editor | Not started | Low |  |  |  | 2026-10-30
F-031 | Workbench | Menu bar (File Edit Selection View Go Run Terminal Help) | Done |  | App | Mouse only |  | 2026-10-30
F-032 | Workbench | Menu bar access keys (Alt+F etc.) | Not started | Low |  |  |  | 2026-10-30
F-033 | Workbench | Explorer toolbar (New File / New Folder / Refresh / Collapse) | Done |  | App | Refresh and Collapse: Collapse unit-tested |  | 2026-10-30
F-034 | Workbench | Explorer right-click menu for folders | Done |  | App |  |  | 2026-10-30
F-035 | Workbench | Explorer right-click menu for files | Done |  | App |  |  | 2026-10-30
F-036 | Workbench | Explorer right-click menu on empty space | Done |  | App |  |  | 2026-10-30
F-037 | Workbench | Explorer Cut / Copy / Paste of files | Partial | Medium | Tests | Unit-tested; not tried by mouse |  | 2026-10-30
F-038 | Workbench | Open to the Side | Done |  | App | Ctrl+Enter with the Explorer focused |  | 2026-10-30
F-039 | Workbench | Find in Folder | Done |  | App |  |  | 2026-10-30
F-040 | Workbench | Tab right-click menu and pinning | Done |  | App |  |  | 2026-10-30
F-041 | Workbench | Split editor groups | Done |  | App | Two groups |  | 2026-10-30
F-042 | Workbench | Settings page | Done |  | App |  |  | 2026-10-30
F-043 | Workbench | Resizable and remembered panels | Done |  | App |  |  | 2026-10-30
F-044 | Workbench | Session restore (open files and carets) | Done |  | App |  |  | 2026-10-30
F-045 | Workbench | Restore unsaved edits after restart | Not started | High |  | Hot exit |  | 2026-10-30
F-046 | Workbench | Restore the second editor group's tabs | Not started | Medium |  |  |  | 2026-10-30
F-047 | Workbench | Drag and drop of tabs | Not started | Medium |  | Files and folders in the Explorer can be dragged (F-097); tabs cannot |  | 2026-10-30
F-048 | Workbench | Multi-root workspaces | Not started | Medium |  | Large architectural change; also needed for Add/Remove Folder from Workspace |  | 2026-10-30
F-049 | Workbench | Image viewer | Done |  | App | PNG JPEG GIF BMP WebP ICO |  | 2026-10-30
F-050 | Workbench | Hex view for binary files | Done |  | App | Read-only; first 256 KiB |  | 2026-10-30
F-051 | Workbench | Explorer menu: Share / Open Changes / Open on Remote / Timeline / Add to Chat | Not started | Low |  | Need remote links and chat features that Forge does not have |  | 2026-10-30
F-052 | Workbench | Exit with unsaved changes warning | Partial | Low | Not verified | Asks once; second Exit discards |  | 2026-10-30
F-053 | Terminal | Integrated terminal with several tabs | Done |  | App |  |  | 2026-10-30
F-054 | Terminal | 5000 lines of scrollback | Done |  | App |  |  | 2026-10-30
F-055 | Terminal | Open terminal in a folder | Done |  | App |  |  | 2026-10-30
F-056 | Language servers | Completion, hover, signature help | Done |  | App |  |  | 2026-10-30
F-057 | Language servers | Go to definition, references, rename, quick fix | Done |  | App |  |  | 2026-10-30
F-058 | Language servers | Diagnostics | Done |  | App |  |  | 2026-10-30
F-059 | Language servers | Servers installed automatically | Partial | Low | App | Several servers (rust-analyzer gopls clangd jdtls csharp-ls ruby-lsp lua-language-server taplo sqls) must be installed by the user |  | 2026-10-30
F-060 | Language servers | Inlay hints | Not started | Medium |  |  |  | 2026-10-30
F-061 | Language servers | Semantic highlighting | Not started | Medium |  |  |  | 2026-10-30
F-062 | Language servers | Code Lens | Not started | Low |  |  |  | 2026-10-30
F-063 | Source control | Stage, commit, push, pull, sync, fetch, stash | Done |  | App |  |  | 2026-10-30
F-064 | Source control | Branches, history, blame | Done |  | App |  |  | 2026-10-30
F-065 | Source control | AI commit messages (OpenAI / Gemini) | Partial | Medium | Tests | Gemini endpoint reachable; a successful generation with a real key was never tested |  | 2026-10-30
F-066 | Source control | Side-by-side diffs | Done |  | App |  |  | 2026-10-30
F-067 | Source control | Hunk and line staging (including new files) | Done |  | App |  |  | 2026-10-30
F-068 | Source control | Discard hunk / selected lines | Done |  | App |  |  | 2026-10-30
F-069 | Source control | Merge-conflict resolution with base column | Done |  | App | Base side cannot be accepted or edited |  | 2026-10-30
F-070 | Source control | Rebase, merge, continue / skip / abort | Done |  | App |  |  | 2026-10-30
F-071 | Source control | Interactive rebase | Partial | Low | App | No edit or break steps; no --rebase-merges |  | 2026-10-30
F-072 | Source control | Cherry-pick and revert | Done |  | App |  |  | 2026-10-30
F-073 | Source control | Login and GPG-passphrase prompts | Done |  | App | Hardware-token PIN prompts not covered |  | 2026-10-30
F-074 | Source control | Cancel a running git operation | Done |  | App |  |  | 2026-10-30
F-075 | Source control | Commit graph and file timeline | Done |  | App | Latest 400 commits and 12 lanes |  | 2026-10-30
F-076 | Source control | Submodules and worktrees | Partial | Low | App | No worktree for a new or remote branch; no per-submodule Source Control view |  | 2026-10-30
F-077 | Source control | Actions on a commit in the graph (checkout / cherry-pick / branch) | Not started | Medium |  |  |  | 2026-10-30
F-078 | Source control | Stash management beyond push and pop | Not started | Low |  |  |  | 2026-10-30
F-079 | Source control | File History and Copy Remote File URL from the Explorer | Done |  | App | GitHub / GitLab / Bitbucket style remotes |  | 2026-10-30
F-080 | Debugging | Python debugging (debugpy) | Done |  | App |  |  | 2026-10-30
F-081 | Debugging | JavaScript / Node debugging | Done |  | App |  |  | 2026-10-30
F-082 | Debugging | Rust debugging (CodeLLDB) | Done |  | App |  |  | 2026-10-30
F-083 | Debugging | Conditional breakpoints | Not started | Medium |  |  |  | 2026-10-30
F-084 | Debugging | Watch expressions | Not started | Medium |  |  |  | 2026-10-30
F-085 | Debugging | More languages | Not started | Low |  |  |  | 2026-10-30
F-086 | Extensions | Install from Open VSX (themes, languages, grammars, snippets) | Done |  | App |  |  | 2026-10-30
F-087 | Extensions | Partial vscode API for running extension code | Partial | Medium | Tests | No third-party extension has been run yet |  | 2026-10-30
F-088 | Extensions | Webviews, tree views, terminals, notebooks, tasks APIs | Not started | Low |  | See docs/EXTENSIONS_PLAN.md |  | 2026-10-30
F-089 | Extensions | Language-feature providers from extensions | Not started | Low |  |  |  | 2026-10-30
F-090 | Text and files | Non-monospace font layout | Not started | Low |  | Layout assumes one cell per character |  | 2026-10-30
F-091 | Text and files | Files that are not UTF-8 | Not started | Low |  | Such files open as a hex dump |  | 2026-10-30
F-092 | Text and files | Files over 64 MiB | Not started | Low |  |  |  | 2026-10-30
F-093 | Highlighting | 29 languages | Done |  | App | Skipped above 4 MiB |  | 2026-10-30
F-094 | Highlighting | Embedded code (script / style in HTML; fenced Markdown) | Partial | Low | App | Not above 512 KiB; not in template strings or style attributes |  | 2026-10-30
F-095 | Packaging | Windows installer | Partial | High | App | dist\Forge-Setup-0.1.0.exe was built before the latest changes; rebuild it |  | 2026-10-30
F-096 | Packaging | Commit the work to git | Not started | High |  | Nothing has been committed |  | 2026-10-30
F-097 | Workbench | Drag and drop files and folders in the Explorer (move; Ctrl copies; asks first) | Done |  | App | Setting explorer.confirmDragAndDrop; drop on a folder, a file (next to it) or the empty area (project folder) |  | 2026-10-30
F-098 | Workbench | Drop files from Windows Explorer into the Explorer (copy) | Partial | Medium | Not verified | Drop handler is wired up; an OS drag could not be tried in testing |  | 2026-10-30
F-099 | Workbench | Open a folder while hovering a drag over it | Not started | Low |  | VS Code expands folders after a short hover |  | 2026-10-30
F-100 | Workbench | Drag several selected items at once | Not started | Low |  | The Explorer has single selection only |  | 2026-10-30
F-101 | Workbench | Sans UI font and monospace code font (editor.fontFamily / workbench.fontFamily) | Done |  | App | Cascadia Mono / Segoe UI by default; no font files are bundled |  | 2026-10-30
F-102 | Workbench | Codicon file and folder icons in the Explorer, tabs and Git lists | Done |  | App | Extension icon themes still take over when chosen |  | 2026-10-30
F-103 | Workbench | Bundled UI and code fonts (so the look is the same on every PC) | Not started | Low |  | Needs font files with a licence that allows it, e.g. Inter and JetBrains Mono (OFL) |  | 2026-10-30
F-104 | Editing | Snippet suggestions in the completion popup (editor.snippetSuggestions) | Done |  | App |  |  | 2026-10-30
F-105 | Editing | Snippet choices dropdown (${1¦a,b¦}) | Done |  | App | Arrows then Enter/Tab |  | 2026-10-30
F-106 | Editing | Snippet variables (clipboard, file, line, local date and time, UUID, RANDOM...) | Done |  | App | Unit-tested; all standard variables |  | 2026-10-30
F-107 | Editing | Snippet transforms (${VAR/regex/format/opts}) | Partial | Low | Tests | Worked out once at insertion; not live as you type |  | 2026-10-30
F-108 | Editing | Configure User Snippets (create per-language / global files, reload on save) | Done |  | App |  |  | 2026-10-30
F-109 | Editing | Snippet tab-stop transforms that follow typing | Not started | Low |  |  |  | 2026-10-30
F-110 | Editing | Expand language-server snippet-format completions | Not started | Medium |  | Servers are told snippets are not supported, so they send plain text |  | 2026-10-30
F-111 | Editing | Built-in snippets for every language (about 290; editor.builtInSnippets) | Done |  | App | Rust, Python, JS/TS/React, HTML, CSS, Go, C/C++, Java, C#, PHP, Ruby, Lua, SQL, shell, YAML, TOML, JSON, Dockerfile, Makefile, Markdown and all-language ones |  | 2026-10-30
F-112 | Editing | Auto closing tags (HTML, XML, JSX, TSX) | Done |  | App | Typing > and </ |  | 2026-10-30
F-113 | Editing | Bracket pair colorization | Done |  | App | Skips strings and line comments; block comments can confuse it |  | 2026-10-30
F-114 | Editing | Word-based suggestions without a language server | Done |  | App |  |  | 2026-10-30
F-115 | Editing | Emmet filters, lorem and the rarer CSS abbreviations | Not started | Low |  |  |  | 2026-10-30
F-116 | Editing | Auto closing tags for Vue / Svelte / PHP files | Partial | Low | Not verified | Works when an extension names the language vue, svelte, astro, handlebars or razor; never tried with one |  | 2026-10-30
F-117 | Editing | Horizontal scrolling of long lines (wheel, Shift+wheel, caret reveal) | Done |  | App | No horizontal scroll bar is drawn; word wrap on turns it off |  | 2026-10-30
F-118 | Workbench | Scrolling the tab strip with the wheel when many tabs are open | Done |  | App | The active tab is brought into view when it changes |  | 2026-10-30
F-119 | Source control | Horizontal scrolling in the side-by-side diff (both columns together) | Done |  | App | Wheel or Shift+wheel; the inline diff is an editor and scrolls like one |  | 2026-10-30
F-120 | Editing | A horizontal scroll bar and dragging to scroll sideways | Not started | Low |  |  |  | 2026-10-30
F-121 | Workbench | Full-page Markdown preview that replaces the source (Ctrl+Shift+V) | Done |  | App | Editing is blocked while it shows |  | 2026-10-30
F-122 | Workbench | Markdown preview: headings anchors, raw HTML blocks (e.g. centred images) and task-list checkboxes | Not started | Low |  | Links to a heading in the same page are not supported; HTML like <p align> shows as text |  | 2026-10-30
F-123 | Workbench | CSV / TSV preview as a table (Ctrl+Shift+V) | Done |  | App | Header row, row numbers, guessed delimiter, quoted fields; first 100,000 rows |  | 2026-10-30
F-124 | Workbench | CSV preview: sort, filter, edit cells, header-less mode | Not started | Low |  |  |  | 2026-10-30
F-125 | Editing | Per-keystroke editing aids kept cheap (bracket depths 4.5x faster, word suggestions 2.7x, tag sync skips text, cached sticky lines) | Done |  | Tests | Timings in the README; benchmarks are ignored tests |  | 2026-10-30
F-126 | Editing | Bracket colouring that recomputes only from the edited line | Not started | Low |  | Today the whole file is re-scanned after each edit (3.6 ms for 25,000 lines) |  | 2026-10-30
F-127 | Editing | Faster CSV parsing for very large files | Not started | Low |  | About 60 MB/s; done once when the preview opens |  | 2026-10-30
F-128 | Workbench | Mouse cursor follows what is under it (I-beam over text and inputs, hand over clickable things and links, resize arrows) | Done |  | App | Checked with the real Windows cursor; Ctrl over a word in the editor shows a hand |  | 2026-10-30
F-129 | Editing | Minimap rebuilt incrementally on each edit (was the biggest per-frame cost in big files) | Done |  | App | 12 ms to 0 ms in a 21,000-line file |  | 2026-10-30
F-130 | Editing | Syntax colours of visible lines cached per frame | Done |  | App |  |  | 2026-10-30
F-131 | Editing | Highlight query compiled once per language | Done |  | Tests | 17 ms saved per extra file of a language |  | 2026-10-30
F-132 | Workbench | Faster startup: git found on a thread, gpg lookup deferred, background tabs parsed when shown | Done |  | App | About 200 ms less before the first frame |  | 2026-10-30
F-133 | Workbench | Profiling aid (FORGE_PROFILE=1) | Done |  | App | Frames per second, time per step, startup phases |  | 2026-10-30
F-134 | Editing | Incremental or deferred syntax reparse for very large files | Not started | Low |  | 4 ms per keystroke at 0.8 MB comes from tree-sitter walking the top-level nodes |  | 2026-10-30
F-135 | Workbench | Faster start of GPUI itself (about 670 ms) | Not started | Low |  | Outside Forge's own code |  | 2026-10-30
F-136 | Terminal | Select text in the terminal and copy it | Done | High | Yes | Drag, double-click word, triple-click line; Ctrl+C / Ctrl+Shift+C / right-click copy; checked in the running app |  | 2026-10-31
F-137 | Terminal | Clickable links in terminal output | Done | High | Yes | URLs open in the browser, existing file paths (with :line:col) open in the editor; underline and hand cursor on hover. URL opening not clicked in testing |  | 2026-10-31
F-138 | Terminal | Auto-scroll while dragging a selection past the edge; selecting scrollback | Not started | Low |  | Selection is cleared when the view scrolls |  | 2026-10-31
F-139 | Workbench | Welcome page for the empty editor (logo, quick actions, recent folders) | Done | Medium | Yes | Actions are clickable; checked in the running app |  | 2026-10-31
F-140 | Workbench | Activity bar as an icon row with a boxed active icon, overflow menu, logo in the menu bar | Done | Medium | Yes | Checked in the running app. Icons for Run and Debug, Testing and Remote are not built (no such views) |  | 2026-10-31
F-141 | Workbench | Preview (replaceable) tabs from a single click in the Explorer | Done | High | Yes | Italic tab; kept on edit or double-click; setting workbench.editor.enablePreview. Checked in the running app |  | 2026-10-31
F-142 | Workbench | Preview tabs from Quick Open, search results and Go to Definition | Not started | Low |  | Only the Explorer opens preview tabs |  | 2026-10-31
F-143 | Editing | Untitled tabs (Ctrl+N) and Save As | Done | High | Yes | System save dialog; tab becomes the file. Checked in the running app. Not built: choosing a language for an untitled tab, restoring untitled tabs after a restart, prompt to save on window close |  | 2026-10-31
F-144 | Workbench | Responsive custom title bar: menus (fold into ... and a hamburger), back/forward, search box, layout toggles, settings, window buttons | Done | Medium | Yes | Checked in the running app at five widths; layout rules unit-tested. Not built: account and Copilot icons, secondary side bar and Customize Layout, submenus inside the ... menu. macOS and Linux not checked |  | 2026-10-31
F-145 | Navigation | Outline view in the Explorer (symbol tree that follows the caret) | Done | High | Yes | LSP symbols, else a text scan (Markdown, Rust, Python, JS/TS, Go...). Checked in the running app; scan unit-tested |  | 2026-10-31
F-146 | Navigation | Outline: sort and filter options, breadcrumbs from the outline, resizing the section | Not started | Low |  | The section has a fixed height and shows symbols in file order |  | 2026-10-31
F-147 | Workbench | Window always opens maximized | Done | Medium | Yes | Checked in the running app. True full screen (F11, no taskbar) is not built |  | 2026-10-31
F-148 | Editing | Language mode picker (status bar) with Auto Detect, and content-based detection | Done | High | Yes | Name, then shebang/markup/shape of the code; embedded languages follow. Checked in the running app; detection unit-tested |  | 2026-10-31
F-149 | Editing | Language mode: associate a file extension with a language, languages from extensions in the picker, remember the choice per file | Not started | Low |  | A manual choice lasts only while the file is open |  | 2026-10-31
F-150 | Editing | Toggle comment works in HTML, CSS, Markdown, XML, JSON and embedded code | Done | High | Yes | HTML, XML, Markdown, CSS: one block comment around the selection (like VS Code's block fallback); line-comment languages: one token per line. Language taken at the caret. Checked in the running app; unit-tested |  | 2026-10-31

## How to use
How to use this tracker
Add a feature | Go to the Features sheet, type in the first empty row under the table (it grows by itself). Give it the next ID (F-097...). Dropdowns appear for Status, Priority and Verified.
Finish a feature | Change Status to Done, set Verified (App = tried in the running editor), and update the Updated date.
Find what is left | Use the filter arrows on the Features header: Status = Partial or Not started, then sort by Priority.
Dashboard | Counts and percentages are formulas over the Features sheet (rows 2 to 500). A new Area needs a new row on the Dashboard: copy an area row and change its name.
Status | Done = built and working. Partial = built with a known gap (see Notes). Not started = not built.
Priority | High / Medium / Low. Filled in for open items only; the values were set by Claude and are yours to change.
Verified | App = checked in the running editor. Tests = unit tests only. Not verified = builds, never run.
Owner / Updated | Free text and a date. Left blank for you to use.
Example row | F-097 ¦ Editing ¦ Bracket pair colorization ¦ Not started ¦ Low ¦ (blank) ¦ Needs tree-sitter bracket queries ¦ (blank) ¦ 2026-11-02